## Agile Product Roadmap
<Mood Tracker> | Sept |  |  | Oct |  |  | Nov
| 1 to 10 | 11 to 20 | 20 to 31 | 1 to 10 | 11 to 20 | 21 to 30 | 1 to 10 | 11 to 20 | 21 to 30
Sprint 1
Sprint 2
Sprint 3
User Interface, Glossary
Initial UML Diagram
User Interface Mockups
User Profile, Login , Sign up fragments
Navigation bar
User search
Mood - create, edit, delete
Map and cluster markers
Database adjustments
Mood History, Filter
Edit Profile
Follow lists, requests
Bugs, Improvements

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.